## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 14 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | DAYS IN NOVEMBER
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Initial Overview Group Meeting | 2 | 1 | 2 | 1 | 100%
Executive Overview [Ismahan] | 2 | 1 | 2 | 1 | 100%
Second Meeting, Grades Received | 4 | 1 | 4 | 1 | 100%
Domains Outline [Gregory] | 4 | 1 | 4 | 2 | 75%
Domains and Schemas Finalized [Fidiana/Nathaniel] | 5 | 1 | 5 | 1 | 100%
Logical and Conceptual Data Model [Fidiana/Nathaniel] | 5 | 1 | 5 | 1 | 100%
Revised Validations [Al Amin/Mohammed] | 6 | 1 | 6 | 2 | 90%
Third Meeting | 7 | 1 | 7 | 1 | 100%
Default Constraints [Gregory/Ismahan] | 7 | 1 | 7 | 1 | 100%
Validations and Domain Edits [Fidiana/Nathaniel] | 8 | 1 | 8 | 1 | 100%
Indexes and Unique Constraints [Gregory/Kabir] | 9 | 1 | 9 | 1 | 100%
Subject Area and Audit Trigger Tables [Fidiana] | 11 | 1 | 11 | 1 | 100%
Themes and Nullability [Fidiana] | 12 | 1 | 12 | 1 | 100%
Audit Table Triggers [Fidiana] | 12 | 2 | 12 | 2 | 100%
Forward Engineering [Al Amin/Fidiana] | 13 | 1 | 13 | 1 | 100%
Revise Executive Overview [Gregory] | 13 | 1 | 13 | 1 | 100%
Revise Progress Tracking [Gregory] | 13 | 1 | 13 | 1 | 100%
Presentation Voice Recordings | 13 | 1 | 13 | 2 | 100%